## Cover
Ministry of Railways — Zonal Project Review
Review date: 21/09/2026
Synthetic demo data
Sheet 'Projects' lists all sanctioned works above ₹150 crore.

## Projects
Proj. Code | Name of the Project | Category | Zone / State | Executing Agency | Sanctioned Cost (Rs. Cr.) | Anticipated Cost (Rs. Cr.) | Exp. Incurred till date (Rs. Cr.) | Sanction Date | Target Date | Revised DOC | % Complete | Bottlenecks
RB/2022/001 | Electrification Bhubaneswar–Cuttack | Railways - Electrification | Odisha | Northern Railway | 3228.3 | 3965.13 | 1479.36 | 19/11/2022 | 18/10/2028 | 14/10/2030 | 0.433 | Law & order; Environment clearance
RB/2020/002 | Gauge Conversion Raipur–Bilaspur | Railways - Gauge Conversion | Chhattisgarh | DFCCIL | 2921.13 | 2921.13 | 3067.19 | 12/10/2020 | 16/09/2025 | 24/09/2026 | 1
RB/2020/003 | Gauge Conversion Vizag–Vizianagaram | Railways - Gauge Conversion | Andhra Pradesh | DFCCIL | 699.44 | 813.39 | 836.88 | 22/07/2020 | 23/11/2025 | 20/07/2026 | 1
RB/2019/004 | New Line Lucknow–Kanpur | Railways - New Line | Uttar Pradesh | DFCCIL | 380.26 | 380.26 | 278.43 | 04/05/2019 | 02/01/2025 | 02/03/2029 | 0.711
RB/2021/005 | Gauge Conversion Mangaluru–Udupi | Railways - Gauge Conversion | Karnataka | RVNL | 622.51 | 925.56 | 583.12 | 10/10/2021 | 24/10/2024 | 01/10/2027 | 0.596 | Design changes; Utility shifting
RB/2022/006 | New Line Bhopal–Itarsi | Railways - New Line | Madhya Pradesh | DFCCIL | 215.25 | 307.94 | 177.21 | 05/10/2022 | 13/11/2026 | 26/04/2030 | 0.524 | Law & order
RB/2025/007 | Gauge Conversion Chennai–Vellore | Railways - Gauge Conversion | Tamil Nadu | East Coast Railway | 2549.22 | 2549.22 | 889.22 | 30/01/2025 | 17/09/2027 | 14/05/2028 | 0.332 | Contractual issues; Design changes
RB/2023/008 | Gauge Conversion Ranchi–Dhanbad | Railways - Gauge Conversion | Jharkhand | East Coast Railway | 7141.52 | 10964.63 | 10402.64 | 10/02/2023 | 31/03/2025 | 20/11/2026 | 0.943 | Law & order; Monsoon / geological surprises
RB/2024/009 | Electrification Dehradun–Rishikesh | Railways - Electrification | Uttarakhand | Northern Railway | 4725.38 | 5877.28 | 2065.31 | 21/01/2024 | 22/08/2029 | 09/04/2030 | 0.346 | Contractual issues; Forest clearance
RB/2018/010 | Electrification Guwahati–Silchar | Railways - Electrification | Assam | IRCON | 8794.12 | 15087.99 | 11986.09 | 27/01/2018 | 06/04/2022 | 28/09/2026 | 0.909 | Rehabilitation & resettlement; Monsoon / geological surprises
RB/2022/011 | New Line Chennai–Vellore | Railways - New Line | Tamil Nadu | IRCON | 2608.87 | 2608.87 | 2294.47 | 04/07/2022 | 18/02/2025 | 27/09/2024 | 1
RB/2022/012 | Gauge Conversion Kochi–Thrissur | Railways - Gauge Conversion | Kerala | East Coast Railway | 273.21 | 273.21 | 275.2 | 30/05/2022 | 19/05/2024 | 31/08/2024 | 1
RB/2018/013 | Doubling Dehradun–Rishikesh | Railways - Doubling | Uttarakhand | DFCCIL | 602.29 | 716.55 | 645.22 | 06/04/2018 | 22/09/2020 | 02/08/2021 | 1
RB/2024/014 | New Line Siliguri–Jalpaiguri | Railways - New Line | West Bengal | Northern Railway | 170.55 | 170.55 | 70.02 | 20/08/2024 | 07/05/2027 | 23/06/2028 | 0.422 | Funding constraints
RB/2023/015 | Electrification Ranchi–Dhanbad | Railways - Electrification | Jharkhand | IRCON | 956.35 | 956.35 | 392.89 | 20/06/2023 | 21/10/2028 | 12/07/2029 | 0.446 | Design changes; Rehabilitation & resettlement
RB/2025/016 | Doubling Hyderabad–Warangal | Railways - Doubling | Telangana | Northern Railway | 421.97 | 421.97 | 157.83 | 29/06/2025 | 09/01/2029 | 03/09/2029 | 0.252
RB/2024/017 | Doubling Patna–Gaya | Railways - Doubling | Bihar | Northern Railway | 11639.23 | 11639.23 | 8862.9 | 22/04/2024 | 23/10/2029 | 30/05/2029 | 0.509
RB/2024/018 | Electrification Bhopal–Itarsi | Railways - Electrification | Madhya Pradesh | Northern Railway | 764.99 | 764.99 | 394.77 | 08/03/2024 | 15/07/2028 | 02/09/2028 | 0.559
RB/2019/019 | Doubling Ranchi–Dhanbad | Railways - Doubling | Jharkhand | DFCCIL | 4027.54 | 5574.41 | 4552.26 | 26/03/2019 | 28/05/2024 | 19/12/2026 | 0.863
RB/2021/020 | Gauge Conversion Ludhiana–Jalandhar | Railways - Gauge Conversion | Punjab | East Coast Railway | 810.32 | 905.43 | 950.7 | 18/09/2021 | 08/10/2023 | 09/04/2024 | 1
RB/2022/021 | Electrification Surat–Vadodara | Railways - Electrification | Gujarat | DFCCIL | 258.35 | 258.35 | 271.27 | 22/06/2022 | 02/05/2026 | 22/10/2026 | 1
RB/2019/022 | New Line Shimla–Kalka | Railways - New Line | Himachal Pradesh | RVNL | 946.55 | 1367.86 | 1436.25 | 20/12/2019 | 06/08/2022 | 13/08/2024 | 1
RB/2023/023 | New Line Dehradun–Rishikesh | Railways - New Line | Uttarakhand | East Coast Railway | 309.32 | 309.32 | 279.73 | 24/08/2023 | 12/09/2025 | 20/11/2026 | 0.917 | Land acquisition
RB/2024/024 | Doubling Rohtak–Hisar | Railways - Doubling | Haryana | IRCON | 4733.31 | 4733.31 | 4406.72 | 07/02/2024 | 21/06/2027 | 10/05/2027 | 0.888
RB/2018/025 | Gauge Conversion Bhubaneswar–Cuttack | Railways - Gauge Conversion | Odisha | Northern Railway | 4026.42 | 4026.42 | 4227.74 | 18/08/2018 | 22/08/2023 | 20/11/2026 | 0.771 | Utility shifting; Rehabilitation & resettlement
RB/2018/026 | New Line Raipur–Bilaspur | Railways - New Line | Chhattisgarh | RVNL | 10427.74 | 10427.74 | 10949.13 | 09/03/2018 | 17/01/2022 | 15/03/2023 | 1
RB/2017/027 | Gauge Conversion Surat–Vadodara | Railways - Gauge Conversion | Gujarat | RVNL | 266.62 | 266.62 | 256.31 | 04/12/2017 | 14/09/2021 | 09/10/2024 | 1 | Utility shifting
RB/2025/028 | New Line Jaipur–Ajmer | Railways - New Line | Rajasthan | Northern Railway | 232.5 | 232.5 | 112.03 | 07/08/2025 | 17/06/2029 | 02/03/2029 | 0.343
RB/2017/029 | Doubling Chennai–Vellore | Railways - Doubling | Tamil Nadu | Northern Railway | 20513.21 | 31632.66 | 26778.52 | 22/08/2017 | 27/02/2022 | 20/11/2026 | 0.955 | Rehabilitation & resettlement; Environment clearance
RB/2017/030 | Gauge Conversion Mangaluru–Udupi | Railways - Gauge Conversion | Karnataka | DFCCIL | 7838.52 | 9955.39 | 9881.53 | 13/08/2017 | 13/02/2023 | 20/11/2026 | 0.996 | Monsoon / geological surprises; Contractual issues
RB/2021/031 | Doubling Hyderabad–Warangal | Railways - Doubling | Telangana | East Coast Railway | 957.27 | 957.27 | 917.79 | 08/08/2021 | 18/02/2025 | 09/06/2026 | 1 | Forest clearance; Law & order
RB/2025/032 | Gauge Conversion Hyderabad–Warangal | Railways - Gauge Conversion | Telangana | RVNL | 10209.9 | 10209.9 | 5495.02 | 11/07/2025 | 27/01/2028 | 06/05/2028 | 0.357 | Contractual issues
RB/2025/033 | Doubling Mangaluru–Udupi | Railways - Doubling | Karnataka | DFCCIL | 162.37 | 203.33 | 44.64 | 23/08/2025 | 09/04/2028 | 20/09/2029 | 0.216 | Contractual issues; Utility shifting
RB/2019/034 | Gauge Conversion Chennai–Vellore | Railways - Gauge Conversion | Tamil Nadu | RVNL | 865.8 | 865.8 | 909.09 | 20/10/2019 | 25/07/2024 | 08/03/2028 | 0.925 | Monsoon / geological surprises; Contractual issues
RB/2022/035 | Electrification Mangaluru–Udupi | Railways - Electrification | Karnataka | RVNL | 916.63 | 1083.01 | 1074.71 | 05/03/2022 | 18/05/2025 | 20/11/2026 | 0.941 | Contractual issues
RB/2017/036 | Doubling Mangaluru–Udupi | Railways - Doubling | Karnataka | IRCON | 2776.35 | 3070.91 | 3116.27 | 22/11/2017 | 27/09/2022 | 02/11/2024 | 1 | Forest clearance; Contractual issues
RB/2018/037 | Gauge Conversion Chennai–Vellore | Railways - Gauge Conversion | Tamil Nadu | RVNL | 18582.26 | 22850.85 | 16346.06 | 01/06/2018 | 07/03/2023 | 22/10/2026 | 0.819 | Funding constraints
RB/2021/038 | Gauge Conversion Ranchi–Dhanbad | Railways - Gauge Conversion | Jharkhand | RVNL | 1624.85 | 1624.85 | 1670.45 | 07/03/2021 | 19/07/2024 | 17/04/2025 | 1
RB/2021/039 | Electrification Lucknow–Kanpur | Railways - Electrification | Uttar Pradesh | Northern Railway | 948.25 | 948.25 | 540.49 | 07/12/2021 | 15/04/2026 | 02/02/2029 | 0.57 | Forest clearance
RB/2020/040 | Gauge Conversion Patna–Gaya | Railways - Gauge Conversion | Bihar | East Coast Railway | 6800.7 | 6800.7 | 6625.88 | 03/09/2020 | 06/12/2025 | 28/01/2026 | 1
RB/2018/041 | Doubling Nagpur–Wardha | Railways - Doubling | Maharashtra | IRCON | 11933.45 | 17150.19 | 18007.7 | 14/01/2018 | 25/09/2021 | 09/03/2026 | 1 | Forest clearance; Contractual issues
RB/2021/042 | New Line Rohtak–Hisar | Railways - New Line | Haryana | DFCCIL | 200.53 | 307.65 | 203.58 | 01/09/2021 | 19/03/2024 | 14/05/2028 | 0.681 | Utility shifting; Environment clearance
RB/2020/043 | Doubling Ludhiana–Jalandhar | Railways - Doubling | Punjab | DFCCIL | 566.08 | 628.27 | 413 | 24/09/2020 | 27/03/2026 | 19/03/2029 | 0.62 | Utility shifting; Law & order
RB/2023/044 | Electrification Nagpur–Wardha | Railways - Electrification | Maharashtra | East Coast Railway | 4163.49 | 5297.84 | 2994.01 | 22/07/2023 | 04/09/2026 | 21/02/2028 | 0.605 | Environment clearance; Law & order
RB/2021/045 | Doubling Siliguri–Jalpaiguri | Railways - Doubling | West Bengal | RVNL | 867.63 | 953.6 | 1001.28 | 14/06/2021 | 19/05/2026 | 04/04/2027 | 0.905
RB/2024/046 | Doubling Guwahati–Silchar | Railways - Doubling | Assam | RVNL | 553.65 | 612.56 | 198.98 | 28/10/2024 | 01/03/2030 | 20/08/2030 | 0.374
RB/2024/047 | Electrification Chennai–Vellore | Railways - Electrification | Tamil Nadu | RVNL | 13607.03 | 13607.03 | 4480.54 | 06/05/2024 | 10/01/2029 | 10/01/2029 | 0.321 | Design changes; Monsoon / geological surprises
RB/2024/048 | Doubling Surat–Vadodara | Railways - Doubling | Gujarat | Northern Railway | 12068.21 | 12507.12 | 9729.75 | 03/02/2024 | 17/06/2027 | 19/09/2027 | 0.715
RB/2019/049 | Electrification Ranchi–Dhanbad | Railways - Electrification | Jharkhand | RVNL | 24577.28 | 24577.28 | 25806.14 | 23/02/2019 | 02/07/2023 | 26/02/2026 | 1 | Land acquisition; Rehabilitation & resettlement
RB/2025/050 | Electrification Mangaluru–Udupi | Railways - Electrification | Karnataka | Northern Railway | 3884.93 | 4901.31 | 676.38 | 09/08/2025 | 21/12/2028 | 21/12/2028 | 0.128 | Contractual issues
RB/2023/051 | Gauge Conversion Shimla–Kalka | Railways - Gauge Conversion | Himachal Pradesh | Northern Railway | 236.51 | 258.08 | 242.11 | 13/04/2023 | 26/06/2026 | 08/10/2026 | 0.937
RB/2024/052 | Electrification Lucknow–Kanpur | Railways - Electrification | Uttar Pradesh | IRCON | 3562.31 | 5403.32 | 2859.69 | 24/09/2024 | 10/08/2027 | 08/11/2029 | 0.344 | Rehabilitation & resettlement; Environment clearance
RB/2019/053 | Gauge Conversion Rohtak–Hisar | Railways - Gauge Conversion | Haryana | IRCON | 5232.75 | 5750.23 | 6037.74 | 25/10/2019 | 12/05/2022 | 22/09/2022 | 1
RB/2023/054 | Electrification Nagpur–Wardha | Railways - Electrification | Maharashtra | East Coast Railway | 6249.39 | 6249.39 | 6123.63 | 08/06/2023 | 22/06/2026 | 04/04/2028 | 0.643 | Rehabilitation & resettlement
RB/2024/055 | Gauge Conversion Nagpur–Wardha | Railways - Gauge Conversion | Maharashtra | East Coast Railway | 24075.37 | 24075.37 | 8777.7 | 04/02/2024 | 19/05/2027 | 26/01/2029 | 0.427 | Law & order; Forest clearance
RB/2018/056 | New Line Vizag–Vizianagaram | Railways - New Line | Andhra Pradesh | East Coast Railway | 16792.79 | 18819.88 | 16717.19 | 29/09/2018 | 31/03/2024 | 22/10/2025 | 1
RB/2019/057 | New Line Bhubaneswar–Cuttack | Railways - New Line | Odisha | Northern Railway | 4196.51 | 4196.51 | 4406.34 | 18/07/2019 | 27/07/2023 | 21/10/2026 | 1
RB/2017/058 | Electrification Bhubaneswar–Cuttack | Railways - Electrification | Odisha | East Coast Railway | 24394.91 | 29140.2 | 30597.21 | 17/11/2017 | 05/04/2020 | 23/08/2021 | 1 | Forest clearance
RB/2021/059 | Electrification Imphal–Jiribam | Railways - Electrification | Manipur | IRCON | 330.57 | 341.65 | 204.42 | 18/09/2021 | 19/06/2027 | 03/04/2028 | 0.638
RB/2021/060 | Electrification Lucknow–Kanpur | Railways - Electrification | Uttar Pradesh | RVNL | 237.43 | 237.43 | 112.12 | 13/06/2021 | 15/09/2026 | 29/12/2029 | 0.492 | Design changes; Forest clearance
RB/2020/061 | Electrification Kochi–Thrissur | Railways - Electrification | Kerala | DFCCIL | 884.75 | 1177.72 | 1218.37 | 30/01/2020 | 15/12/2022 | 16/10/2024 | 1 | Monsoon / geological surprises
RB/2021/062 | New Line Jammu–Udhampur | Railways - New Line | Jammu & Kashmir | DFCCIL | 1328.95 | 1481.31 | 1289.61 | 26/03/2021 | 10/03/2024 | 16/06/2025 | 1 | Law & order; Environment clearance
RB/2021/063 | New Line Chennai–Vellore | Railways - New Line | Tamil Nadu | IRCON | 14863.7 | 14863.7 | 15606.89 | 03/03/2021 | 14/08/2024 | 07/06/2024 | 1
RB/2023/064 | Gauge Conversion Jaipur–Ajmer | Railways - Gauge Conversion | Rajasthan | East Coast Railway | 4272.65 | 4460.94 | 2426.41 | 14/12/2023 | 16/04/2029 | 16/04/2029 | 0.506
RB/2020/065 | Doubling Mangaluru–Udupi | Railways - Doubling | Karnataka | RVNL | 588.58 | 649.12 | 573.56 | 07/11/2020 | 14/06/2025 | 19/06/2025 | 1
RB/2023/066 | New Line Patna–Gaya | Railways - New Line | Bihar | RVNL | 19247.07 | 19247.07 | 15099.98 | 16/02/2023 | 27/03/2027 | 17/04/2028 | 0.503 | Utility shifting; Design changes
RB/2023/067 | Doubling Raipur–Bilaspur | Railways - Doubling | Chhattisgarh | East Coast Railway | 24283.18 | 24283.18 | 13057.13 | 19/11/2023 | 22/11/2028 | 13/11/2028 | 0.555
RB/2017/068 | New Line Jaipur–Ajmer | Railways - New Line | Rajasthan | RVNL | 7144.95 | 7144.95 | 6844.46 | 14/12/2017 | 26/06/2021 | 20/10/2023 | 1 | Design changes; Land acquisition
RB/2022/069 | Doubling Raipur–Bilaspur | Railways - Doubling | Chhattisgarh | East Coast Railway | 2528.77 | 2528.77 | 2369.19 | 05/05/2022 | 04/01/2028 | 07/07/2027 | 0.914
RB/2021/070 | Electrification Vizag–Vizianagaram | Railways - Electrification | Andhra Pradesh | IRCON | 2515.96 | 2515.96 | 1801.33 | 06/02/2021 | 19/08/2024 | 03/10/2027 | 0.718 | Land acquisition; Environment clearance