## Project Report
Project Monitoring Report — Central Sector Infrastructure Projects (₹150 crore & above)
Synthetic demo data · Report month: September 2026 · Costs in ₹ crore
S.No. | Project ID | Project Name | Ministry/Department | Sector | State | Implementing Agency | Original Cost (₹ Cr) | Latest Approved / Revised Cost (₹ Cr) | Cumulative Expenditure (₹ Cr) | Date of Approval | Original Date of Commissioning | Anticipated Date of Commissioning | Physical Progress (%) | Status | Reasons for Delay
1 | RAI-2026-0001 | Doubling Siliguri–Jalpaiguri | Ministry of Railways | Railways | West Bengal | Northern Railway | 22605.83 | 29940.6 | 22801.84 | 2021-07-14 | 2026-03-20 | Sep-2028 | 72.1 | Delayed | Contractual issues, Rehabilitation & resettlement
2 | POW-2026-0002 | Bhopal Hydro Electric Project | Ministry of Power | Power | Madhya Pradesh | NHPC | 968.97 | 968.97 | 852.13 | 2023-01-27 | 2025-07-15 | Jun-2025 | 100 | Completed
3 | RAI-2026-0003 | Electrification Dehradun–Rishikesh | Ministry of Railways | Railways | Uttarakhand | Northern Railway | 2886.54 | 2886.54 | 3030.87 | 2021-01-21 | 2023-09-08 | Jul-2025 | 100 | Completed | Rehabilitation & resettlement
4 | HIG-2026-0004 | Lucknow–Kanpur Expressway Pkg-89 | Ministry of Road Transport & Highways | Road Transport & Highways | Uttar Pradesh | NHAI | 8815.95 | 8815.95 | 2809.79 | 2025-04-19 | 2029-10-25 | Oct-2029 | 23.3 | On schedule
5 | RAI-2026-0005 | New Line Nagpur–Wardha | Ministry of Railways | Railways | Maharashtra | IRCON | 3014.11 | 3148.06 | 3111.05 | 2018-01-01 | 2020-04-20 | Aug-2020 | 100 | Completed
6 | SHA-2026-0006 | Siliguri–Jalpaiguri River Link Canal | Ministry of Jal Shakti | Water Resources | West Bengal | WAPCOS | 913.81 | 913.81 | 284.37 | 2025-04-20 | 2027-04-10 | Aug-2027 | 20.7 | Delayed | Funding constraints, Land acquisition
7 | RAI-2026-0007 | New Line Bhopal–Itarsi | Ministry of Railways | Railways | Madhya Pradesh | RVNL | 4796.24 | 5809.95 | 6100.45 | 2019-08-19 | 2022-03-06 | Dec-2022 | 100 | Completed
8 | HIG-2026-0008 | Mangaluru–Udupi Expressway Pkg-14 | Ministry of Road Transport & Highways | Road Transport & Highways | Karnataka | NHAI | 542.8 | 668.77 | 272.21 | 2023-05-31 | 2029-01-29 | Oct-2030 | 46.4 | Delayed | Funding constraints, Utility shifting
9 | GAS-2026-0009 | Imphal Refinery Expansion | Ministry of Petroleum & Natural Gas | Petroleum & Natural Gas | Manipur | ONGC | 961.72 | 988.49 | 882.68 | 2019-05-15 | 2023-08-22 | May-2023 | 100 | Completed
10 | POW-2026-0010 | Guwahati–Silchar 765kV Transmission Line | Ministry of Power | Power | Assam | THDC | 732.56 | 934.85 | 781.38 | 2021-03-15 | 2025-05-23 | Jan-2027 | 80.4 | Delayed | Law & order
11 | RAI-2026-0011 | Doubling Rohtak–Hisar | Ministry of Railways | Railways | Haryana | IRCON | 924.09 | 947.61 | 975.19 | 2021-08-11 | 2026-06-16 | Dec-2026 | 94.5 | Delayed
12 | GAS-2026-0012 | Siliguri–Jalpaiguri Natural Gas Pipeline | Ministry of Petroleum & Natural Gas | Petroleum & Natural Gas | West Bengal | IOCL | 2334.95 | 2334.95 | 337.5 | 2025-11-21 | 2030-05-29 | May-2030 | 13.8 | On schedule
13 | AFF-2026-0013 | Rohtak Metro Phase-III | Ministry of Housing & Urban Affairs | Urban Development | Haryana | DMRC | 13551.77 | 13812.21 | 13376.45 | 2021-10-27 | 2025-10-06 | Aug-2025 | 100 | Completed
14 | GAS-2026-0014 | Jaipur Refinery Expansion | Ministry of Petroleum & Natural Gas | Petroleum & Natural Gas | Rajasthan | IOCL | 243.76 | 243.76 | 249.21 | 2021-03-13 | 2024-04-26 | Jun-2026 | 100 | Completed | Rehabilitation & resettlement, Forest clearance
15 | HIG-2026-0015 | 4-laning of NH-93 Shimla–Kalka | Ministry of Road Transport & Highways | Road Transport & Highways | Himachal Pradesh | NHIDCL | 2887.94 | 3217.95 | 3122.53 | 2021-11-25 | 2025-08-06 | Nov-2026 | 95.8 | Delayed
16 | HIG-2026-0016 | Bypass at Chennai | Ministry of Road Transport & Highways | Road Transport & Highways | Tamil Nadu | NHAI | 4023.29 | 4023.29 | 3535.64 | 2022-09-18 | 2028-05-19 | Nov-2027 | 86.7 | On schedule
17 | HIG-2026-0017 | Vizag–Vizianagaram Expressway Pkg-97 | Ministry of Road Transport & Highways | Road Transport & Highways | Andhra Pradesh | NHAI | 186.36 | 255.5 | 179.75 | 2022-01-11 | 2025-12-21 | May-2027 | 78.4 | Delayed | Rehabilitation & resettlement, Monsoon / geological surprises
18 | WAT-2026-0018 | Deep Draught Berth at Shimla | Ministry of Ports, Shipping & Waterways | Shipping & Ports | Himachal Pradesh | IWAI | 19122.62 | 19122.62 | 6496.74 | 2025-07-19 | 2029-01-29 | Jan-2029 | 38.4 | On schedule
19 | STE-2026-0019 | Lucknow Pellet Plant | Ministry of Steel | Steel | Uttar Pradesh | NMDC | 14874.74 | 16779.76 | 4510.85 | 2025-07-16 | 2030-02-20 | Oct-2031 | 20.4 | Delayed
20 | RAI-2026-0020 | Doubling Guwahati–Silchar | Ministry of Railways | Railways | Assam | IRCON | 290.15 | 460.33 | 456.15 | 2021-04-13 | 2025-06-21 | Oct-2027 | 62.5 | Delayed | Land acquisition, Contractual issues
21 | POW-2026-0021 | Lucknow–Kanpur 765kV Transmission Line | Ministry of Power | Power | Uttar Pradesh | THDC | 3232.91 | 3897.24 | 4092.1 | 2020-05-14 | 2023-05-29 | Jul-2024 | 100 | Completed | Rehabilitation & resettlement
22 | POW-2026-0022 | Bhopal–Itarsi 765kV Transmission Line | Ministry of Power | Power | Madhya Pradesh | PGCIL | 23704.02 | 23704.02 | 19799.94 | 2021-10-18 | 2026-07-24 | Dec-2026 | 95.7 | Delayed
23 | SHA-2026-0023 | Raipur Dam Rehabilitation | Ministry of Jal Shakti | Water Resources | Chhattisgarh | State Irrigation Dept | 1835.7 | 1835.7 | 857.25 | 2022-09-21 | 2028-08-20 | Mar-2032 | 46.9 | Delayed | Design changes
24 | RAI-2026-0024 | Electrification Mangaluru–Udupi | Ministry of Railways | Railways | Karnataka | DFCCIL | 2726.91 | 3397.58 | 3399.36 | 2018-08-13 | 2023-06-18 | Nov-2026 | 97.2 | Delayed | Rehabilitation & resettlement
25 | HIG-2026-0025 | Bhopal–Itarsi Expressway Pkg-53 | Ministry of Road Transport & Highways | Road Transport & Highways | Madhya Pradesh | NHAI | 5840.54 | 5840.54 | 4449.69 | 2024-10-20 | 2028-05-02 | May-2028 | 79.2 | On schedule
26 | GAS-2026-0026 | Lucknow Refinery Expansion | Ministry of Petroleum & Natural Gas | Petroleum & Natural Gas | Uttar Pradesh | ONGC | 20916.11 | 20916.11 | 20944.89 | 2018-05-02 | 2021-03-17 | Aug-2023 | 100 | Completed | Design changes, Environment clearance
27 | RAI-2026-0027 | New Line Kochi–Thrissur | Ministry of Railways | Railways | Kerala | Northern Railway | 4562.51 | 4562.51 | 4036.43 | 2024-05-05 | 2027-01-20 | Mar-2027 | 70 | Delayed | Law & order, Contractual issues
28 | TEL-2026-0028 | BharatNet Phase-I Patna Circle | Department of Telecommunications | Telecommunications | Bihar | BBNL | 7396.26 | 7396.26 | 4954.28 | 2021-10-31 | 2027-05-03 | Sep-2027 | 63.5 | Delayed | Rehabilitation & resettlement, Utility shifting
29 | AFF-2026-0029 | Ranchi–Dhanbad RRTS Corridor | Ministry of Housing & Urban Affairs | Urban Development | Jharkhand | BMRCL | 2193.53 | 3051.66 | 3204.24 | 2019-01-07 | 2021-09-23 | Jun-2023 | 100 | Completed | Funding constraints, Forest clearance
30 | GAS-2026-0030 | Dehradun–Rishikesh Natural Gas Pipeline | Ministry of Petroleum & Natural Gas | Petroleum & Natural Gas | Uttarakhand | BPCL | 22720.69 | 23159.29 | 10722.65 | 2024-09-25 | 2028-05-07 | Jul-2028 | 52.3 | Delayed
31 | STE-2026-0031 | Vizag Pellet Plant | Ministry of Steel | Steel | Andhra Pradesh | NMDC | 335 | 357.31 | 375.18 | 2018-05-27 | 2020-10-13 | Sep-2020 | 100 | Completed
32 | WEL-2026-0032 | Mangaluru Critical Care Block | Ministry of Health & Family Welfare | Health & Family Welfare | Karnataka | CPWD | 15889.13 | 18126.57 | 6158.91 | 2024-06-04 | 2030-02-03 | Jul-2030 | 31.4 | Delayed | Utility shifting
33 | POW-2026-0033 | Vizag–Vizianagaram 765kV Transmission Line | Ministry of Power | Power | Andhra Pradesh | THDC | 22223.09 | 24197.74 | 20991.17 | 2024-02-14 | 2026-07-03 | Sep-2026 | 91.9 | Delayed
34 | POW-2026-0034 | Surat Super Thermal Power Project Stage-II | Ministry of Power | Power | Gujarat | THDC | 11251.06 | 12701.77 | 5228.3 | 2025-05-14 | 2027-09-01 | Sep-2027 | 45.8 | Delayed
35 | WEL-2026-0035 | AIIMS Vizag | Ministry of Health & Family Welfare | Health & Family Welfare | Andhra Pradesh | HSCC | 3471.61 | 3471.61 | 3645.19 | 2023-06-03 | 2027-01-13 | Jun-2026 | 100 | Completed
36 | SHA-2026-0036 | Rohtak Dam Rehabilitation | Ministry of Jal Shakti | Water Resources | Haryana | State Irrigation Dept | 12354.65 | 12354.65 | 2392.19 | 2025-05-23 | 2029-04-02 | Apr-2032 | 20.4 | Delayed
37 | AVI-2026-0037 | New Terminal Building at Ranchi Airport | Ministry of Civil Aviation | Civil Aviation | Jharkhand | Airports Authority of India | 371.5 | 445.32 | 462.31 | 2017-06-16 | 2022-01-21 | Oct-2023 | 100 | Completed | Design changes
38 | GAS-2026-0038 | Jaipur Refinery Expansion | Ministry of Petroleum & Natural Gas | Petroleum & Natural Gas | Rajasthan | IOCL | 312.92 | 312.92 | 289.07 | 2020-10-05 | 2024-11-13 | Nov-2025 | 100 | Completed
39 | POW-2026-0039 | Lucknow–Kanpur 765kV Transmission Line | Ministry of Power | Power | Uttar Pradesh | NTPC | 17340.82 | 17340.82 | 1503.37 | 2025-12-01 | 2030-02-08 | Dec-2030 | 8.8 | Delayed | Law & order
40 | GAS-2026-0040 | Chennai Refinery Expansion | Ministry of Petroleum & Natural Gas | Petroleum & Natural Gas | Tamil Nadu | GAIL | 5991.13 | 5991.13 | 6290.69 | 2021-07-27 | 2025-11-03 | Mar-2025 | 100 | Completed
41 | AVI-2026-0041 | New Terminal Building at Ludhiana Airport | Ministry of Civil Aviation | Civil Aviation | Punjab | Airports Authority of India | 6391.52 | 6391.52 | 3129.66 | 2021-01-14 | 2026-12-14 | May-2030 | 52.6 | Delayed
42 | GAS-2026-0042 | Vizag Refinery Expansion | Ministry of Petroleum & Natural Gas | Petroleum & Natural Gas | Andhra Pradesh | GAIL | 3155.28 | 4934.25 | 4999.05 | 2017-11-20 | 2020-07-07 | May-2023 | 100 | Completed | Land acquisition, Design changes
43 | STE-2026-0043 | Vizag Steel Plant Modernisation | Ministry of Steel | Steel | Andhra Pradesh | NMDC | 18770.9 | 25921.06 | 1694.61 | 2025-12-03 | 2031-10-03 | Oct-2031 | 7.5 | On schedule
44 | HIG-2026-0044 | Bypass at Surat | Ministry of Road Transport & Highways | Road Transport & Highways | Gujarat | NHIDCL | 1350.63 | 2180.29 | 922.76 | 2022-08-22 | 2028-01-23 | Jan-2028 | 40.4 | On schedule | Forest clearance, Design changes
45 | WAT-2026-0045 | Jammu Inland Waterway Terminal | Ministry of Ports, Shipping & Waterways | Shipping & Ports | Jammu & Kashmir | IWAI | 681.09 | 761.69 | 753.88 | 2022-06-23 | 2025-08-06 | Apr-2026 | 100 | Completed
46 | AFF-2026-0046 | Jammu–Udhampur RRTS Corridor | Ministry of Housing & Urban Affairs | Urban Development | Jammu & Kashmir | MMRCL | 1317.05 | 1784.27 | 1873.48 | 2022-11-15 | 2025-08-01 | Nov-2026 | 87.6 | Delayed
47 | AFF-2026-0047 | Ludhiana Metro Phase-I | Ministry of Housing & Urban Affairs | Urban Development | Punjab | BMRCL | 24836.85 | 24836.85 | 19447.96 | 2017-10-12 | 2023-07-13 | Nov-2026 | 84.9 | Delayed | Funding constraints
48 | GAS-2026-0048 | Vizag–Vizianagaram Natural Gas Pipeline | Ministry of Petroleum & Natural Gas | Petroleum & Natural Gas | Andhra Pradesh | BPCL | 815.97 | 1222.61 | 1283.74 | 2017-10-18 | 2021-10-27 | Dec-2025 | 100 | Completed | Forest clearance
49 | TEL-2026-0049 | BharatNet Phase-III Bhopal Circle | Department of Telecommunications | Telecommunications | Madhya Pradesh | BSNL | 1110.85 | 1312.78 | 646.16 | 2022-08-14 | 2028-04-14 | Apr-2028 | 46.9 | On schedule | Funding constraints
50 | POW-2026-0050 | Imphal–Jiribam 765kV Transmission Line | Ministry of Power | Power | Manipur | NHPC | 4541.89 | 4541.89 | 2750.37 | 2022-01-27 | 2027-06-30 | Jul-2028 | 68.5 | Delayed | Forest clearance
51 | POW-2026-0051 | Surat Hydro Electric Project | Ministry of Power | Power | Gujarat | NHPC | 968.32 | 968.32 | 849.77 | 2021-03-01 | 2023-07-19 | Mar-2023 | 100 | Completed
52 | RAI-2026-0052 | New Line Dehradun–Rishikesh | Ministry of Railways | Railways | Uttarakhand | East Coast Railway | 3516.15 | 3516.15 | 3691.96 | 2018-08-15 | 2021-01-01 | Apr-2021 | 100 | Completed
53 | WEL-2026-0053 | Vizag Critical Care Block | Ministry of Health & Family Welfare | Health & Family Welfare | Andhra Pradesh | CPWD | 356.61 | 383.32 | 402.49 | 2018-04-03 | 2023-12-03 | Sep-2025 | 100 | Completed | Law & order
54 | SHA-2026-0054 | Vizag–Vizianagaram River Link Canal | Ministry of Jal Shakti | Water Resources | Andhra Pradesh | WAPCOS | 22369.34 | 29121.28 | 30577.34 | 2020-08-22 | 2024-02-03 | Jul-2026 | 100 | Completed | Rehabilitation & resettlement, Utility shifting
55 | RAI-2026-0055 | New Line Nagpur–Wardha | Ministry of Railways | Railways | Maharashtra | RVNL | 937.68 | 1425.58 | 853.9 | 2020-12-16 | 2026-01-19 | Feb-2030 | 54.6 | Delayed | Forest clearance, Law & order
56 | STE-2026-0056 | Raipur Pellet Plant | Ministry of Steel | Steel | Chhattisgarh | RINL | 16333.24 | 20887.89 | 16622.76 | 2020-10-02 | 2025-02-08 | Apr-2027 | 75.9 | Delayed | Design changes, Rehabilitation & resettlement
57 | HIG-2026-0057 | Ludhiana–Jalandhar Expressway Pkg-25 | Ministry of Road Transport & Highways | Road Transport & Highways | Punjab | NHIDCL | 4784.52 | 4784.52 | 5023.75 | 2023-02-06 | 2025-07-25 | Feb-2026 | 100 | Completed
58 | RAI-2026-0058 | Doubling Bhopal–Itarsi | Ministry of Railways | Railways | Madhya Pradesh | RVNL | 559.43 | 1157.29 | 1034.67 | 2017-11-01 | 2023-05-04 | Jul-2029 | 59.5 | Delayed | Forest clearance
59 | AFF-2026-0059 | Ludhiana–Jalandhar RRTS Corridor | Ministry of Housing & Urban Affairs | Urban Development | Punjab | MMRCL | 264.82 | 312.83 | 321.47 | 2018-06-21 | 2023-11-22 | Feb-2025 | 100 | Completed
60 | RAI-2026-0060 | New Line Patna–Gaya | Ministry of Railways | Railways | Bihar | East Coast Railway | 2228.4 | 2545.81 | 2411.2 | 2020-03-24 | 2023-12-04 | Oct-2024 | 100 | Completed
61 | HIG-2026-0061 | Bypass at Raipur | Ministry of Road Transport & Highways | Road Transport & Highways | Chhattisgarh | NHIDCL | 24378.06 | 34133.99 | 32335.98 | 2020-12-11 | 2023-11-26 | Oct-2025 | 100 | Completed | Environment clearance, Contractual issues
62 | WEL-2026-0062 | Ludhiana Critical Care Block | Ministry of Health & Family Welfare | Health & Family Welfare | Punjab | HSCC | 2979.99 | 3657.1 | 3163.65 | 2019-04-03 | 2022-02-16 | Mar-2023 | 100 | Completed | Environment clearance, Contractual issues
63 | RAI-2026-0063 | Electrification Jaipur–Ajmer | Ministry of Railways | Railways | Rajasthan | DFCCIL | 4794.83 | 5454.19 | 4819.09 | 2022-09-19 | 2027-04-26 | Jan-2028 | 61.5 | Delayed
64 | WEL-2026-0064 | AIIMS Jaipur | Ministry of Health & Family Welfare | Health & Family Welfare | Rajasthan | HSCC | 21895.47 | 21895.47 | 22460.52 | 2017-12-08 | 2022-12-12 | Mar-2022 | 100 | Completed
65 | SHA-2026-0065 | Patna Irrigation Project | Ministry of Jal Shakti | Water Resources | Bihar | WAPCOS | 10547.21 | 11857.75 | 12450.64 | 2018-09-19 | 2024-05-20 | Nov-2026 | 97.9 | Delayed | Contractual issues
66 | HIG-2026-0066 | 4-laning of NH-81 Raipur–Bilaspur | Ministry of Road Transport & Highways | Road Transport & Highways | Chhattisgarh | NHAI | 1846.86 | 2547.77 | 2675.16 | 2021-09-23 | 2023-11-12 | Mar-2025 | 100 | Completed | Design changes, Monsoon / geological surprises
67 | RAI-2026-0067 | New Line Bhopal–Itarsi | Ministry of Railways | Railways | Madhya Pradesh | DFCCIL | 910.92 | 1178.39 | 959.16 | 2019-09-24 | 2025-03-26 | Oct-2026 | 84.5 | Delayed | Design changes, Law & order
68 | WEL-2026-0068 | AIIMS Raipur | Ministry of Health & Family Welfare | Health & Family Welfare | Chhattisgarh | HSCC | 10100.04 | 12523.7 | 8909.16 | 2024-05-21 | 2026-11-07 | Nov-2027 | 70.1 | Delayed | Rehabilitation & resettlement
69 | RAI-2026-0069 | Gauge Conversion Patna–Gaya | Ministry of Railways | Railways | Bihar | East Coast Railway | 602.82 | 602.82 | 595.48 | 2022-05-06 | 2025-04-20 | Jun-2026 | 100 | Completed | Contractual issues
70 | HIG-2026-0070 | 4-laning of NH-77 Hyderabad–Warangal | Ministry of Road Transport & Highways | Road Transport & Highways | Telangana | NHAI | 16639.08 | 16639.08 | 15663.13 | 2021-12-25 | 2024-12-09 | Dec-2025 | 100 | Completed
71 | AFF-2026-0071 | Kochi–Thrissur RRTS Corridor | Ministry of Housing & Urban Affairs | Urban Development | Kerala | BMRCL | 366.44 | 366.44 | 124.52 | 2025-05-01 | 2028-04-15 | Dec-2028 | 22.8 | Delayed | Funding constraints, Rehabilitation & resettlement
72 | AFF-2026-0072 | Rohtak Metro Phase-III | Ministry of Housing & Urban Affairs | Urban Development | Haryana | NCRTC | 823.49 | 823.49 | 853.2 | 2018-01-03 | 2021-08-15 | Sep-2025 | 100 | Completed | Forest clearance, Funding constraints
73 | SHA-2026-0073 | Bhubaneswar Irrigation Project | Ministry of Jal Shakti | Water Resources | Odisha | NWDA | 17767.82 | 23184.64 | 11151.79 | 2020-05-26 | 2024-11-01 | Aug-2032 | 54.8 | Delayed
74 | RAI-2026-0074 | Gauge Conversion Chennai–Vellore | Ministry of Railways | Railways | Tamil Nadu | IRCON | 213.42 | 242.1 | 242.32 | 2018-11-09 | 2021-05-27 | Apr-2022 | 100 | Completed
75 | POW-2026-0075 | Ranchi Super Thermal Power Project Stage-II | Ministry of Power | Power | Jharkhand | PGCIL | 662.1 | 662.1 | 677.62 | 2018-02-01 | 2020-06-20 | Jul-2020 | 100 | Completed
76 | SHA-2026-0076 | Surat Irrigation Project | Ministry of Jal Shakti | Water Resources | Gujarat | NWDA | 4186.36 | 5228.13 | 2759.79 | 2024-02-07 | 2027-05-22 | Jul-2027 | 58.6 | Delayed | Contractual issues, Monsoon / geological surprises
77 | STE-2026-0077 | Surat Pellet Plant | Ministry of Steel | Steel | Gujarat | RINL | 417.07 | 417.07 | 91.36 | 2026-01-31 | 2030-02-09 | Sep-2029 | 16.1 | On schedule
78 | SHA-2026-0078 | Shimla Irrigation Project | Ministry of Jal Shakti | Water Resources | Himachal Pradesh | State Irrigation Dept | 757.48 | 990.96 | 1002.08 | 2017-11-23 | 2022-01-31 | Sep-2024 | 100 | Completed
79 | RAI-2026-0079 | Gauge Conversion Jammu–Udhampur | Ministry of Railways | Railways | Jammu & Kashmir | East Coast Railway | 3890.87 | 3890.87 | 4085.41 | 2018-12-09 | 2023-11-13 | Nov-2026 | 100 | Completed | Law & order, Funding constraints
80 | RAI-2026-0080 | Doubling Rohtak–Hisar | Ministry of Railways | Railways | Haryana | East Coast Railway | 1187.02 | 1651.41 | 1230.2 | 2021-09-02 | 2026-02-08 | Jun-2028 | 69.1 | Delayed | Land acquisition
81 | RAI-2026-0081 | Gauge Conversion Dehradun–Rishikesh | Ministry of Railways | Railways | Uttarakhand | RVNL | 2370.17 | 2370.17 | 2200.37 | 2023-06-20 | 2026-08-03 | Feb-2026 | 100 | Completed
82 | HIG-2026-0082 | Shimla–Kalka Expressway Pkg-63 | Ministry of Road Transport & Highways | Road Transport & Highways | Himachal Pradesh | NHIDCL | 750.83 | 750.83 | 788.37 | 2017-09-05 | 2020-03-23 | Apr-2021 | 100 | Completed | Utility shifting
83 | HIG-2026-0083 | Bypass at Dehradun | Ministry of Road Transport & Highways | Road Transport & Highways | Uttarakhand | NHIDCL | 13788.79 | 14919.57 | 15665.55 | 2018-06-28 | 2021-02-12 | Jan-2021 | 100 | Completed
84 | POW-2026-0084 | Guwahati Hydro Electric Project | Ministry of Power | Power | Assam | THDC | 15102.71 | 18137.91 | 6261.11 | 2024-11-26 | 2028-07-08 | Feb-2029 | 31.7 | Delayed | Monsoon / geological surprises, Environment clearance
85 | RAI-2026-0085 | New Line Shimla–Kalka | Ministry of Railways | Railways | Himachal Pradesh | East Coast Railway | 823.18 | 1068.9 | 976.46 | 2021-10-26 | 2025-04-08 | Mar-2027 | 92.1 | Delayed | Rehabilitation & resettlement
86 | SHA-2026-0086 | Imphal–Jiribam River Link Canal | Ministry of Jal Shakti | Water Resources | Manipur | WAPCOS | 3044.62 | 3044.62 | 1823.42 | 2025-02-22 | 2027-02-12 | Aug-2027 | 60.3 | Delayed
87 | HIG-2026-0087 | Mangaluru–Udupi Expressway Pkg-84 | Ministry of Road Transport & Highways | Road Transport & Highways | Karnataka | NHIDCL | 501.42 | 501.42 | 526.49 | 2018-01-09 | 2023-06-12 | Aug-2022 | 100 | Completed
88 | HIG-2026-0088 | Bypass at Dehradun | Ministry of Road Transport & Highways | Road Transport & Highways | Uttarakhand | NHIDCL | 4291.57 | 5495.47 | 4708.87 | 2018-03-28 | 2020-11-12 | Nov-2023 | 100 | Completed | Monsoon / geological surprises, Land acquisition
89 | POW-2026-0089 | Imphal Hydro Electric Project | Ministry of Power | Power | Manipur | NHPC | 2322.08 | 2627.95 | 2759.35 | 2023-07-20 | 2026-05-05 | Jun-2027 | 75.9 | Delayed
90 | WAT-2026-0090 | Bhopal Inland Waterway Terminal | Ministry of Ports, Shipping & Waterways | Shipping & Ports | Madhya Pradesh | Deendayal Port | 20078.53 | 22390.73 | 23510.27 | 2018-02-06 | 2022-02-15 | Sep-2022 | 100 | Completed
91 | HIG-2026-0091 | Bhubaneswar–Cuttack Expressway Pkg-23 | Ministry of Road Transport & Highways | Road Transport & Highways | Odisha | NHAI | 8972.75 | 8972.75 | 6182.13 | 2022-06-19 | 2026-01-29 | Aug-2027 | 78.1 | Delayed | Design changes, Monsoon / geological surprises
92 | RAI-2026-0092 | Electrification Patna–Gaya | Ministry of Railways | Railways | Bihar | DFCCIL | 2948.52 | 3465.09 | 2443.44 | 2020-10-15 | 2024-12-23 | Dec-2026 | 73.6 | Delayed | Monsoon / geological surprises, Design changes
93 | SHA-2026-0093 | Mangaluru–Udupi River Link Canal | Ministry of Jal Shakti | Water Resources | Karnataka | WAPCOS | 194.98 | 226.74 | 15.25 | 2026-03-04 | 2030-09-09 | Jan-2031 | 7.4 | Delayed
94 | WEL-2026-0094 | AIIMS Mangaluru | Ministry of Health & Family Welfare | Health & Family Welfare | Karnataka | CPWD | 531.69 | 531.69 | 558.27 | 2019-06-15 | 2022-03-31 | Sep-2022 | 100 | Completed
95 | RAI-2026-0095 | Gauge Conversion Ludhiana–Jalandhar | Ministry of Railways | Railways | Punjab | Northern Railway | 12270.2 | 12270.2 | 10603.28 | 2019-12-31 | 2023-12-10 | Dec-2025 | 100 | Completed
96 | HIG-2026-0096 | Ranchi–Dhanbad Expressway Pkg-42 | Ministry of Road Transport & Highways | Road Transport & Highways | Jharkhand | NHIDCL | 1896.33 | 1979.51 | 1662 | 2023-01-21 | 2026-08-03 | Apr-2027 | 77.3 | Delayed
97 | POW-2026-0097 | Jammu Super Thermal Power Project Stage-II | Ministry of Power | Power | Jammu & Kashmir | SJVN | 13680.33 | 14634.6 | 15366.33 | 2022-05-12 | 2024-05-01 | Aug-2024 | 100 | Completed
98 | GAS-2026-0098 | Chennai Refinery Expansion | Ministry of Petroleum & Natural Gas | Petroleum & Natural Gas | Tamil Nadu | BPCL | 459.37 | 647.43 | 659.35 | 2018-12-10 | 2024-06-11 | Oct-2027 | 77.9 | Delayed | Utility shifting
99 | HIG-2026-0099 | Bypass at Jammu | Ministry of Road Transport & Highways | Road Transport & Highways | Jammu & Kashmir | NHIDCL | 14966.38 | 17092.83 | 14167.44 | 2022-10-28 | 2026-05-10 | Nov-2026 | 92.8 | Delayed
100 | AFF-2026-0100 | Ranchi–Dhanbad RRTS Corridor | Ministry of Housing & Urban Affairs | Urban Development | Jharkhand | MMRCL | 22802.97 | 22802.97 | 20635.24 | 2022-05-06 | 2024-06-24 | Feb-2024 | 100 | Completed
101 | AFF-2026-0101 | Rohtak Metro Phase-III | Ministry of Housing & Urban Affairs | Urban Development | Haryana | MMRCL | 941.98 | 941.98 | 989.08 | 2018-12-22 | 2023-12-26 | Jan-2024 | 100 | Completed
102 | WEL-2026-0102 | AIIMS Shimla | Ministry of Health & Family Welfare | Health & Family Welfare | Himachal Pradesh | HSCC | 15929.62 | 16870.7 | 17216.65 | 2023-12-31 | 2026-12-15 | Nov-2026 | 93 | On schedule
103 | AFF-2026-0103 | Hyderabad Metro Phase-III | Ministry of Housing & Urban Affairs | Urban Development | Telangana | NCRTC | 690.72 | 1096.93 | 214.26 | 2025-07-01 | 2030-07-05 | Jul-2030 | 15.1 | On schedule | Contractual issues, Land acquisition
104 | AFF-2026-0104 | Raipur Metro Phase-I | Ministry of Housing & Urban Affairs | Urban Development | Chhattisgarh | NCRTC | 6947.51 | 10400.35 | 10920.37 | 2018-04-20 | 2023-11-20 | Nov-2028 | 73.2 | Delayed | Forest clearance
105 | RAI-2026-0105 | New Line Kochi–Thrissur | Ministry of Railways | Railways | Kerala | DFCCIL | 3788.42 | 5659.65 | 5930.09 | 2020-06-17 | 2023-04-03 | Jun-2025 | 100 | Completed | Funding constraints, Forest clearance
106 | RAI-2026-0106 | Gauge Conversion Dehradun–Rishikesh | Ministry of Railways | Railways | Uttarakhand | IRCON | 489.08 | 489.08 | 501.43 | 2019-04-09 | 2024-01-13 | Feb-2025 | 100 | Completed
107 | AFF-2026-0107 | Imphal Metro Phase-I | Ministry of Housing & Urban Affairs | Urban Development | Manipur | BMRCL | 199.6 | 199.6 | 209.58 | 2020-06-02 | 2023-03-19 | Oct-2022 | 100 | Completed
108 | POW-2026-0108 | Rohtak Hydro Electric Project | Ministry of Power | Power | Haryana | THDC | 2943.67 | 2943.67 | 3090.85 | 2022-02-12 | 2027-04-17 | Jul-2026 | 100 | Completed
109 | POW-2026-0109 | Shimla Hydro Electric Project | Ministry of Power | Power | Himachal Pradesh | PGCIL | 13799.49 | 15552.1 | 6440.68 | 2024-09-28 | 2029-05-05 | Nov-2029 | 37.8 | Delayed
110 | HIG-2026-0110 | 4-laning of NH-18 Jaipur–Ajmer | Ministry of Road Transport & Highways | Road Transport & Highways | Rajasthan | NHIDCL | 11195.28 | 11195.28 | 11494.2 | 2023-07-31 | 2026-07-15 | Feb-2026 | 100 | Completed
111 | POW-2026-0111 | Vizag Super Thermal Power Project Stage-II | Ministry of Power | Power | Andhra Pradesh | NHPC | 1038.24 | 1063.56 | 1024.51 | 2024-03-20 | 2026-05-09 | Feb-2026 | 100 | Completed
112 | WAT-2026-0112 | Ludhiana Inland Waterway Terminal | Ministry of Ports, Shipping & Waterways | Shipping & Ports | Punjab | JNPA | 4388.23 | 4388.23 | 2726.78 | 2025-07-21 | 2027-12-08 | Sep-2027 | 65.5 | On schedule
113 | HIG-2026-0113 | Hyderabad–Warangal Expressway Pkg-51 | Ministry of Road Transport & Highways | Road Transport & Highways | Telangana | NHAI | 859.53 | 859.53 | 666.26 | 2024-03-13 | 2026-09-29 | Mar-2027 | 79.7 | Delayed
114 | COA-2026-0114 | Dehradun Opencast Expansion | Ministry of Coal | Coal | Uttarakhand | SCCL | 14329.31 | 14329.31 | 12861.88 | 2020-12-10 | 2026-07-12 | Oct-2029 | 67.2 | Delayed | Funding constraints
115 | RAI-2026-0115 | Electrification Hyderabad–Warangal | Ministry of Railways | Railways | Telangana | IRCON | 1601.3 | 1784.79 | 1202.58 | 2023-12-02 | 2026-12-16 | Mar-2027 | 73.6 | Delayed
116 | RAI-2026-0116 | Gauge Conversion Guwahati–Silchar | Ministry of Railways | Railways | Assam | Northern Railway | 12940.13 | 17078.23 | 10078.11 | 2024-05-05 | 2026-04-25 | Jul-2027 | 65.6 | Delayed | Law & order, Contractual issues
117 | RAI-2026-0117 | Doubling Shimla–Kalka | Ministry of Railways | Railways | Himachal Pradesh | East Coast Railway | 354.86 | 438.24 | 197.02 | 2023-06-20 | 2026-11-01 | Aug-2028 | 51.5 | Delayed | Environment clearance
118 | GAS-2026-0118 | Patna Refinery Expansion | Ministry of Petroleum & Natural Gas | Petroleum & Natural Gas | Bihar | GAIL | 727.14 | 787.73 | 801.92 | 2019-09-22 | 2022-02-08 | Oct-2021 | 100 | Completed
119 | HIG-2026-0119 | 4-laning of NH-10 Chennai–Vellore | Ministry of Road Transport & Highways | Road Transport & Highways | Tamil Nadu | NHAI | 434.41 | 492.61 | 357.93 | 2022-05-01 | 2027-09-02 | Oct-2027 | 70.3 | Delayed
120 | RAI-2026-0120 | Gauge Conversion Vizag–Vizianagaram | Ministry of Railways | Railways | Andhra Pradesh | Northern Railway | 2770.74 | 4283.17 | 377.29 | 2024-10-30 | 2030-07-31 | Jul-2030 | 9.1 | On schedule | Rehabilitation & resettlement
121 | HIG-2026-0121 | Rohtak–Hisar Expressway Pkg-88 | Ministry of Road Transport & Highways | Road Transport & Highways | Haryana | NHIDCL | 354.9 | 441.12 | 463.18 | 2021-04-28 | 2024-02-12 | Oct-2025 | 100 | Completed | Monsoon / geological surprises
122 | SHA-2026-0122 | Surat Irrigation Project | Ministry of Jal Shakti | Water Resources | Gujarat | NWDA | 299.65 | 372.24 | 319.67 | 2020-09-02 | 2023-12-16 | May-2025 | 100 | Completed | Monsoon / geological surprises, Utility shifting
123 | RAI-2026-0123 | Doubling Jaipur–Ajmer | Ministry of Railways | Railways | Rajasthan | DFCCIL | 5990.63 | 5990.63 | 5361.9 | 2020-06-26 | 2025-04-01 | Jan-2026 | 100 | Completed
124 | WAT-2026-0124 | Hyderabad Inland Waterway Terminal | Ministry of Ports, Shipping & Waterways | Shipping & Ports | Telangana | Deendayal Port | 1530.46 | 1530.46 | 694.47 | 2024-10-19 | 2029-02-25 | Oct-2028 | 47.2 | On schedule
125 | WEL-2026-0125 | Bhopal Critical Care Block | Ministry of Health & Family Welfare | Health & Family Welfare | Madhya Pradesh | CPWD | 2402.75 | 2656.6 | 2789.43 | 2020-06-05 | 2025-08-08 | Nov-2026 | 95.9 | Delayed
126 | TEL-2026-0126 | 4G Saturation Bhubaneswar Circle | Department of Telecommunications | Telecommunications | Odisha | BSNL | 4643.47 | 5562.79 | 5719.33 | 2021-03-03 | 2024-11-12 | Sep-2025 | 100 | Completed
127 | POW-2026-0127 | Ludhiana–Jalandhar 765kV Transmission Line | Ministry of Power | Power | Punjab | NHPC | 7743.58 | 7743.58 | 8130.76 | 2021-12-21 | 2026-04-29 | Sep-2025 | 100 | Completed
128 | WAT-2026-0128 | Deep Draught Berth at Nagpur | Ministry of Ports, Shipping & Waterways | Shipping & Ports | Maharashtra | JNPA | 395.11 | 395.11 | 414.87 | 2019-06-06 | 2022-07-20 | Jun-2024 | 100 | Completed | Environment clearance
129 | STE-2026-0129 | Hyderabad Pellet Plant | Ministry of Steel | Steel | Telangana | RINL | 396.24 | 396.24 | 416.05 | 2023-03-14 | 2027-06-21 | Nov-2026 | 98 | On schedule
130 | GAS-2026-0130 | Hyderabad LPG Import Terminal | Ministry of Petroleum & Natural Gas | Petroleum & Natural Gas | Telangana | HPCL | 4503.63 | 4618.93 | 2911.16 | 2024-10-09 | 2027-04-27 | May-2027 | 66.6 | Delayed
131 | RAI-2026-0131 | Doubling Hyderabad–Warangal | Ministry of Railways | Railways | Telangana | Northern Railway | 729.44 | 1205.64 | 808.21 | 2020-08-11 | 2023-10-25 | Sep-2027 | 74.6 | Delayed | Utility shifting, Funding constraints
132 | POW-2026-0132 | Vizag Hydro Electric Project | Ministry of Power | Power | Andhra Pradesh | PGCIL | 285.24 | 285.24 | 184.8 | 2023-05-20 | 2028-09-20 | Mar-2028 | 68.9 | On schedule
133 | COA-2026-0133 | Ranchi Coal Washery | Ministry of Coal | Coal | Jharkhand | Coal India Ltd | 266.42 | 266.42 | 268.09 | 2022-01-06 | 2024-09-22 | Apr-2024 | 100 | Completed
134 | POW-2026-0134 | Chennai–Vellore 765kV Transmission Line | Ministry of Power | Power | Tamil Nadu | PGCIL | 693 | 737.13 | 513.05 | 2023-02-28 | 2028-01-03 | Apr-2028 | 72.5 | Delayed
135 | SHA-2026-0135 | Hyderabad–Warangal River Link Canal | Ministry of Jal Shakti | Water Resources | Telangana | NWDA | 21591.55 | 21591.55 | 22671.13 | 2017-09-26 | 2022-10-30 | Sep-2024 | 100 | Completed | Utility shifting
136 | AFF-2026-0136 | Mangaluru–Udupi RRTS Corridor | Ministry of Housing & Urban Affairs | Urban Development | Karnataka | DMRC | 401.14 | 437.07 | 355.4 | 2021-09-29 | 2025-10-08 | May-2027 | 78.2 | Delayed | Contractual issues, Utility shifting
137 | AFF-2026-0137 | Mangaluru Metro Phase-I | Ministry of Housing & Urban Affairs | Urban Development | Karnataka | DMRC | 364.56 | 364.56 | 376.1 | 2020-12-28 | 2026-11-27 | May-2026 | 100 | Completed
138 | GAS-2026-0138 | Rohtak Refinery Expansion | Ministry of Petroleum & Natural Gas | Petroleum & Natural Gas | Haryana | ONGC | 2627.84 | 2627.84 | 2142.45 | 2020-08-10 | 2025-01-16 | Apr-2027 | 88.5 | Delayed | Funding constraints, Rehabilitation & resettlement
139 | GAS-2026-0139 | Lucknow LPG Import Terminal | Ministry of Petroleum & Natural Gas | Petroleum & Natural Gas | Uttar Pradesh | ONGC | 4818.34 | 5473.56 | 342.62 | 2026-02-19 | 2031-08-22 | Aug-2032 | 6.6 | Delayed
140 | AFF-2026-0140 | Bhubaneswar–Cuttack RRTS Corridor | Ministry of Housing & Urban Affairs | Urban Development | Odisha | DMRC | 304.71 | 304.71 | 314.25 | 2021-05-16 | 2025-08-23 | Oct-2025 | 100 | Completed
141 | SHA-2026-0141 | Shimla Dam Rehabilitation | Ministry of Jal Shakti | Water Resources | Himachal Pradesh | NWDA | 2855.43 | 2855.43 | 2609.91 | 2020-05-07 | 2023-08-20 | Sep-2024 | 100 | Completed | Contractual issues
142 | SHA-2026-0142 | Bhubaneswar Irrigation Project | Ministry of Jal Shakti | Water Resources | Odisha | WAPCOS | 3190 | 5535.04 | 3839.96 | 2019-10-02 | 2023-10-11 | Apr-2028 | 63.2 | Delayed | Funding constraints
143 | WEL-2026-0143 | AIIMS Jaipur | Ministry of Health & Family Welfare | Health & Family Welfare | Rajasthan | CPWD | 20550.99 | 23692.09 | 23756.39 | 2020-05-19 | 2025-11-19 | May-2027 | 91.2 | Delayed
144 | HIG-2026-0144 | Imphal–Jiribam Expressway Pkg-47 | Ministry of Road Transport & Highways | Road Transport & Highways | Manipur | NHIDCL | 8216.99 | 8216.99 | 8583.86 | 2024-02-17 | 2026-09-04 | Oct-2026 | 97.8 | Delayed
145 | RAI-2026-0145 | Gauge Conversion Guwahati–Silchar | Ministry of Railways | Railways | Assam | Northern Railway | 21633.43 | 38141.94 | 3361.55 | 2025-05-23 | 2030-04-27 | Jul-2035 | 9.7 | Delayed | Monsoon / geological surprises
146 | GAS-2026-0146 | Bhubaneswar LPG Import Terminal | Ministry of Petroleum & Natural Gas | Petroleum & Natural Gas | Odisha | ONGC | 169.54 | 169.54 | 163.57 | 2018-09-20 | 2023-04-27 | Dec-2022 | 100 | Completed
147 | SHA-2026-0147 | Bhubaneswar Irrigation Project | Ministry of Jal Shakti | Water Resources | Odisha | WAPCOS | 3004.64 | 4616.43 | 4847.25 | 2019-07-25 | 2022-04-10 | Aug-2024 | 100 | Completed | Monsoon / geological surprises, Funding constraints
148 | SHA-2026-0148 | Bhubaneswar–Cuttack River Link Canal | Ministry of Jal Shakti | Water Resources | Odisha | WAPCOS | 1328.83 | 1328.83 | 257.59 | 2024-08-08 | 2029-09-11 | Sep-2029 | 20.7 | On schedule | Environment clearance
149 | RAI-2026-0149 | New Line Imphal–Jiribam | Ministry of Railways | Railways | Manipur | DFCCIL | 19779.11 | 24619.63 | 13378.44 | 2023-07-14 | 2028-01-19 | Apr-2028 | 55.1 | Delayed | Land acquisition
150 | RAI-2026-0150 | Gauge Conversion Jammu–Udhampur | Ministry of Railways | Railways | Jammu & Kashmir | RVNL | 13788.69 | 21356.59 | 8256.46 | 2019-09-20 | 2025-04-21 | Apr-2034 | 43.1 | Delayed | Contractual issues
151 | SHA-2026-0151 | Rohtak Irrigation Project | Ministry of Jal Shakti | Water Resources | Haryana | NWDA | 549.09 | 549.09 | 576.54 | 2020-05-30 | 2023-02-14 | Jun-2024 | 100 | Completed | Land acquisition
152 | HIG-2026-0152 | 4-laning of NH-31 Nagpur–Wardha | Ministry of Road Transport & Highways | Road Transport & Highways | Maharashtra | NHIDCL | 747.52 | 834.87 | 804.26 | 2018-04-04 | 2022-08-11 | Jun-2022 | 100 | Completed
153 | RAI-2026-0153 | Gauge Conversion Rohtak–Hisar | Ministry of Railways | Railways | Haryana | RVNL | 915.74 | 950.95 | 998.43 | 2019-09-20 | 2024-06-25 | Mar-2025 | 100 | Completed
154 | SHA-2026-0154 | Surat Dam Rehabilitation | Ministry of Jal Shakti | Water Resources | Gujarat | WAPCOS | 17598.37 | 23119.68 | 21582.59 | 2017-09-22 | 2022-11-25 | Oct-2025 | 100 | Completed | Utility shifting, Design changes
155 | RAI-2026-0155 | New Line Ludhiana–Jalandhar | Ministry of Railways | Railways | Punjab | RVNL | 12473.39 | 14161.21 | 13375.76 | 2022-04-26 | 2024-12-11 | May-2025 | 100 | Completed
156 | HIG-2026-0156 | 4-laning of NH-83 Imphal–Jiribam | Ministry of Road Transport & Highways | Road Transport & Highways | Manipur | NHAI | 830.71 | 830.71 | 872.25 | 2020-03-15 | 2023-03-30 | Mar-2023 | 100 | Completed
157 | RAI-2026-0157 | Electrification Vizag–Vizianagaram | Ministry of Railways | Railways | Andhra Pradesh | DFCCIL | 2961.2 | 2961.2 | 2727.69 | 2022-01-18 | 2025-06-01 | Oct-2027 | 67.7 | Delayed
158 | HIG-2026-0158 | 4-laning of NH-4 Patna–Gaya | Ministry of Road Transport & Highways | Road Transport & Highways | Bihar | NHAI | 13506.51 | 20081.18 | 15604.85 | 2022-05-18 | 2026-12-23 | Mar-2029 | 53 | Delayed
159 | SHA-2026-0159 | Guwahati–Silchar River Link Canal | Ministry of Jal Shakti | Water Resources | Assam | WAPCOS | 231.97 | 379.66 | 321.21 | 2019-05-16 | 2024-08-17 | Feb-2029 | 53.6 | Delayed | Monsoon / geological surprises
160 | SHA-2026-0160 | Hyderabad Irrigation Project | Ministry of Jal Shakti | Water Resources | Telangana | WAPCOS | 4595.41 | 4595.41 | 4012.08 | 2021-09-20 | 2023-12-09 | Mar-2026 | 100 | Completed
161 | POW-2026-0161 | Patna Hydro Electric Project | Ministry of Power | Power | Bihar | SJVN | 180.22 | 180.22 | 157.33 | 2021-02-17 | 2023-08-06 | May-2023 | 100 | Completed
162 | HIG-2026-0162 | 4-laning of NH-43 Shimla–Kalka | Ministry of Road Transport & Highways | Road Transport & Highways | Himachal Pradesh | NHAI | 394.49 | 583.88 | 613.07 | 2019-01-18 | 2022-06-01 | Aug-2025 | 100 | Completed | Law & order, Monsoon / geological surprises
163 | AFF-2026-0163 | Chennai–Vellore RRTS Corridor | Ministry of Housing & Urban Affairs | Urban Development | Tamil Nadu | BMRCL | 2447.95 | 2447.95 | 776.61 | 2024-09-28 | 2029-03-06 | Oct-2029 | 35.3 | Delayed | Utility shifting
164 | AFF-2026-0164 | Bhubaneswar–Cuttack RRTS Corridor | Ministry of Housing & Urban Affairs | Urban Development | Odisha | DMRC | 372.59 | 423.88 | 441.63 | 2018-03-15 | 2020-07-02 | Sep-2020 | 100 | Completed
165 | RAI-2026-0165 | Electrification Imphal–Jiribam | Ministry of Railways | Railways | Manipur | Northern Railway | 1748.61 | 1748.61 | 1836.04 | 2020-06-01 | 2024-03-12 | Jun-2024 | 100 | Completed
166 | RAI-2026-0166 | Gauge Conversion Siliguri–Jalpaiguri | Ministry of Railways | Railways | West Bengal | Northern Railway | 14685.47 | 15096.14 | 15649.01 | 2020-06-16 | 2023-02-01 | Apr-2023 | 100 | Completed
167 | AFF-2026-0167 | Jammu–Udhampur RRTS Corridor | Ministry of Housing & Urban Affairs | Urban Development | Jammu & Kashmir | NCRTC | 5973.78 | 9416.94 | 3828.82 | 2023-08-11 | 2028-04-16 | Jul-2030 | 31.1 | Delayed | Law & order
168 | AVI-2026-0168 | Bhopal Greenfield Airport | Ministry of Civil Aviation | Civil Aviation | Madhya Pradesh | Airports Authority of India | 262.79 | 262.79 | 275.93 | 2018-03-27 | 2022-09-02 | Aug-2023 | 100 | Completed
169 | POW-2026-0169 | Imphal–Jiribam 765kV Transmission Line | Ministry of Power | Power | Manipur | SJVN | 12272.98 | 12272.98 | 5982.6 | 2023-06-08 | 2027-10-15 | Jan-2030 | 48.9 | Delayed | Law & order
170 | RAI-2026-0170 | Electrification Hyderabad–Warangal | Ministry of Railways | Railways | Telangana | Northern Railway | 7715.08 | 10192.08 | 10701.68 | 2019-12-22 | 2025-03-25 | Nov-2026 | 99.9 | Delayed
171 | AFF-2026-0171 | Jaipur Metro Phase-I | Ministry of Housing & Urban Affairs | Urban Development | Rajasthan | MMRCL | 11629.93 | 12706.78 | 3225.99 | 2024-12-24 | 2029-05-02 | May-2029 | 25.2 | On schedule | Contractual issues, Forest clearance
172 | HIG-2026-0172 | Nagpur–Wardha Expressway Pkg-90 | Ministry of Road Transport & Highways | Road Transport & Highways | Maharashtra | NHIDCL | 2644.38 | 2810.21 | 2467.87 | 2022-03-07 | 2024-03-26 | Feb-2024 | 100 | Completed
173 | AFF-2026-0173 | Mangaluru–Udupi RRTS Corridor | Ministry of Housing & Urban Affairs | Urban Development | Karnataka | NCRTC | 2041.15 | 2043.22 | 2145.38 | 2017-11-25 | 2022-03-04 | Oct-2022 | 100 | Completed
174 | HIG-2026-0174 | 4-laning of NH-81 Surat–Vadodara | Ministry of Road Transport & Highways | Road Transport & Highways | Gujarat | NHIDCL | 16912.01 | 19404.65 | 17327.81 | 2019-05-31 | 2024-08-02 | Oct-2024 | 100 | Completed
175 | AVI-2026-0175 | Raipur Greenfield Airport | Ministry of Civil Aviation | Civil Aviation | Chhattisgarh | Airports Authority of India | 5916.37 | 5916.37 | 5929.53 | 2024-06-22 | 2027-02-07 | Sep-2026 | 100 | Completed
176 | POW-2026-0176 | Bhubaneswar Hydro Electric Project | Ministry of Power | Power | Odisha | NHPC | 4918.22 | 4918.22 | 5164.13 | 2021-03-03 | 2023-11-18 | Jul-2023 | 100 | Completed
177 | HIG-2026-0177 | Patna–Gaya Expressway Pkg-12 | Ministry of Road Transport & Highways | Road Transport & Highways | Bihar | NHAI | 630.79 | 740.05 | 719.25 | 2019-06-06 | 2025-01-05 | Aug-2026 | 100 | Completed
178 | RAI-2026-0178 | Doubling Guwahati–Silchar | Ministry of Railways | Railways | Assam | DFCCIL | 4914.52 | 4914.52 | 748.99 | 2025-12-07 | 2031-01-10 | Jan-2031 | 10.2 | On schedule | Rehabilitation & resettlement, Land acquisition
179 | HIG-2026-0179 | Bypass at Ranchi | Ministry of Road Transport & Highways | Road Transport & Highways | Jharkhand | NHAI | 7331.86 | 7889.3 | 8283.77 | 2018-12-17 | 2024-11-15 | Dec-2026 | 84.8 | Delayed | Rehabilitation & resettlement, Land acquisition
180 | COA-2026-0180 | Lucknow Opencast Expansion | Ministry of Coal | Coal | Uttar Pradesh | Coal India Ltd | 3870.67 | 4800.6 | 5040.63 | 2017-06-01 | 2021-10-08 | Jun-2023 | 100 | Completed | Utility shifting, Contractual issues
|  | Total |  |  |  |  | 1083906.94 | 1241825.79 | 918763.32